## Read Me
NEXORA Phase 1 Procurement Test Control Pack
Document IDs: NEXORA-TC-PROC-001 ¦ NEXORA-RTM-PROC-001 ¦ NEXORA-TER-PROC-001 ¦ NEXORA-DL-PROC-001
Purpose | Control detailed test cases, requirements traceability, manual/automated execution and defects for NEXORA Phase 1 Procurement.
Standards alignment | Tailored to ISO/IEC/IEEE 29119-2:2021 test processes and ISO/IEC/IEEE 29119-3:2021 test documentation. Alignment is not formal certification.
Permanent IDs | Reuse the same Test Case ID in manual evidence, Playwright titles, defect records and reports.
Execution rule | Manually verify and stabilise a scenario before marking it Automated.
Status values | Not Run, Pass, Fail, Blocked, Not Applicable.
Phase 1 scope | Supplier, Warehouse, Purchase Request, Approval, Purchase Order, Goods Receipt, Inventory, cross-cutting controls and end-to-end flow.
Out of scope | Invoice/AP/payment, later ERP modules, production-scale performance/security, AI/RAG/LLM/LangGraph and data migration.
Security | Never store passwords, tokens, cookies, secrets or production personal data in this workbook.

## Requirements
Requirements Baseline
Requirement ID | Area | Requirement statement | Risk | Status
SUP-REQ-001 | Supplier | Create a supplier with a unique supplier code and valid mandatory data | Critical | Approved
SUP-REQ-002 | Supplier | Validate mandatory fields, formats, boundaries and whitespace | High | Approved
SUP-REQ-003 | Supplier | Prevent duplicate supplier records according to configured uniqueness rules | Critical | Approved
SUP-REQ-004 | Supplier | View, search and edit supplier details with persisted changes | High | Approved
SUP-REQ-005 | Supplier | Activate or deactivate a supplier and enforce downstream restrictions | Critical | Approved
WH-REQ-001 | Warehouse | Create, view and select an active warehouse | High | Approved
WH-REQ-002 | Warehouse | Prevent duplicate warehouse codes and invalid warehouse data | High | Approved
PR-REQ-001 | Purchase Request | Create and save a purchase request with valid header and line data | Critical | Approved
PR-REQ-002 | Purchase Request | Validate mandatory fields, quantities and request line completeness | Critical | Approved
PR-REQ-003 | Purchase Request | View and edit a purchase request while its status permits editing | High | Approved
PR-REQ-004 | Purchase Request | Submit a valid draft purchase request exactly once | Critical | Approved
PR-REQ-005 | Purchase Request | Cancel an eligible purchase request and prevent invalid reuse | High | Approved
PR-REQ-006 | Purchase Request | Enforce the approved purchase-request status transition model | Critical | Approved
APR-REQ-001 | Approval | Present submitted requests to an authorised approver | Critical | Approved
APR-REQ-002 | Approval | Approve or reject an eligible request and require an appropriate comment where configured | Critical | Approved
APR-REQ-003 | Approval | Enforce approver permissions and segregation of duties | Critical | Approved
APR-REQ-004 | Approval | Maintain immutable approval actor, timestamp, decision and comments history | High | Approved
APR-REQ-005 | Approval | Prevent duplicate or stale approval actions | Critical | Approved
PO-REQ-001 | Purchase Order | Create a purchase order only from an eligible approved request | Critical | Approved
PO-REQ-002 | Purchase Order | Calculate line totals and order total accurately | Critical | Approved
PO-REQ-003 | Purchase Order | View and edit a purchase order while rules permit | High | Approved
PO-REQ-004 | Purchase Order | Require reapproval when an approved purchase order is materially changed | Critical | Approved
PO-REQ-005 | Purchase Order | Cancel an eligible purchase order and block prohibited downstream activity | High | Approved
PO-REQ-006 | Purchase Order | Prevent duplicate purchase-order creation and preserve source linkage | Critical | Approved
GRN-REQ-001 | Goods Receipt | Receive eligible purchase-order quantities into the selected warehouse | Critical | Approved
GRN-REQ-002 | Goods Receipt | Support full and partial receipt while maintaining remaining quantity | Critical | Approved
GRN-REQ-003 | Goods Receipt | Prevent over-receipt, zero/negative quantities and duplicate receipt submission | Critical | Approved
GRN-REQ-004 | Goods Receipt | Record receipt number, user, timestamp, PO and warehouse references | High | Approved
INV-REQ-001 | Inventory | Increase on-hand inventory exactly once after a valid goods receipt | Critical | Approved
INV-REQ-002 | Inventory | Update the correct item and warehouse without affecting unrelated stock | Critical | Approved
INV-REQ-003 | Inventory | Maintain an auditable inventory transaction linked to the goods receipt | High | Approved
SEC-REQ-001 | Security | Enforce authentication and session/token validity for protected procurement resources | Critical | Approved
SEC-REQ-002 | Security | Enforce object-level and role-based authorisation for every procurement action | Critical | Approved
SEC-REQ-003 | Security | Validate and safely handle malicious or unexpected input | Critical | Approved
SEC-REQ-004 | Security | Protect browser-originated state-changing requests and apply secure cross-origin controls | High | Approved
SEC-REQ-005 | Security | Prevent credential, token, personal and commercially sensitive data exposure | Critical | Approved
SEC-REQ-006 | Security | Apply rate limiting and abuse protection to authentication and sensitive actions | High | Approved
SEC-REQ-007 | Security | Maintain tamper-resistant security and approval audit events | Critical | Approved
SEC-REQ-008 | Security | Prevent unsafe mass assignment of restricted fields | Critical | Approved
SEC-REQ-009 | Security | Use appropriate transport, browser and API security controls | High | Approved
SEC-REQ-010 | Security | Manage dependencies, secrets and application logs without known critical exposure | High | Approved
SYS-REQ-001 | Cross-cutting | Return meaningful API and UI errors without exposing sensitive information | High | Approved
SYS-REQ-002 | Cross-cutting | Record document status history consistently across procurement documents | High | Approved
SYS-REQ-003 | Cross-cutting | Prevent duplicate records during retry, double-click and concurrent submission | Critical | Approved
SYS-REQ-004 | Cross-cutting | Enforce authenticated role-based access to procurement actions | Critical | Approved
E2E-REQ-001 | End-to-End | Complete Supplier to Inventory procurement flow with traceable document linkage | Critical | Approved

## Test Cases
Detailed Phase 1 Procurement Test Cases
Test Case ID | Requirement ID | Feature | Title | Type | Priority | Preconditions | Test steps | Expected result | Target layer | Automation status
SUP-001 | SUP-REQ-001 | Supplier | Create supplier with valid mandatory data | Positive | Critical | Admin authenticated; supplier code unused | Enter valid supplier data; save; search and open record | One supplier is created and all values persist | Manual then UI/API | Planned
SUP-002 | SUP-REQ-002 | Supplier | Submit supplier form with all mandatory fields empty | Negative | High | Admin on create form | Leave fields empty and save | Clear field-level validation appears; no record created | UI | Planned
SUP-003 | SUP-REQ-002 | Supplier | Reject invalid supplier email format | Negative | High | Admin on create form | Enter invalid email with otherwise valid data; save | Invalid email is rejected; no record created | UI/API | Planned
SUP-004 | SUP-REQ-003 | Supplier | Prevent duplicate supplier code | Negative | Critical | Supplier code already exists | Create another supplier using same code | Request rejected consistently; original record unchanged | UI/API/DB | Planned
SUP-005 | SUP-REQ-004 | Supplier | Search and view created supplier | Positive | High | Supplier exists | Search by code/name; open details | Correct supplier and persisted values are displayed | UI | Planned
SUP-006 | SUP-REQ-004 | Supplier | Edit eligible supplier details | Positive | High | Active supplier exists | Edit permitted fields; save; reopen | Only intended fields change; audit metadata updates | UI/API/DB | Planned
SUP-007 | SUP-REQ-005 | Supplier | Deactivate an active supplier | State transition | Critical | Active supplier exists | Deactivate and confirm | Status becomes inactive and history is recorded | UI/API/DB | Planned
SUP-008 | SUP-REQ-005 | Supplier | Prevent inactive supplier use in new procurement | Negative | Critical | Supplier is inactive | Attempt to select/use supplier in PR or PO | Inactive supplier is unavailable or transaction is rejected | UI/API | Planned
SUP-009 | SUP-REQ-005 | Supplier | Reactivate an inactive supplier | State transition | High | Inactive supplier exists | Activate and confirm | Status becomes active and supplier becomes eligible | UI/API | Planned
SUP-010 | SUP-REQ-002 | Supplier | Trim leading and trailing whitespace | Boundary | Medium | Admin on create form | Enter padded code/name and save | Stored business values follow trimming rule | UI/API/DB | Planned
SUP-011 | SYS-REQ-003 | Supplier | Prevent duplicate supplier on repeated submission | Concurrency | High | Valid supplier form complete | Double-click Save or repeat identical request | At most one supplier is committed | UI/API/DB | Planned
WH-001 | WH-REQ-001 | Warehouse | Create and view active warehouse | Positive | High | Authorised user authenticated | Create valid warehouse; search and open | Warehouse persists and is selectable | UI/API/DB | Planned
WH-002 | WH-REQ-002 | Warehouse | Prevent duplicate warehouse code | Negative | High | Warehouse code exists | Submit same code again | Duplicate rejected; one record remains | API/DB | Planned
WH-003 | WH-REQ-001 | Warehouse | Select correct warehouse in procurement transaction | Integration | Critical | Two active warehouses exist | Select target warehouse during receipt | Transaction retains selected warehouse ID | UI/API/DB | Planned
PR-001 | PR-REQ-001 | Purchase Request | Create valid draft purchase request | Positive | Critical | Active supplier/item/warehouse data available | Enter valid header and line; save draft | One Draft request is created with correct values | UI/API/DB | Planned
PR-002 | PR-REQ-002 | Purchase Request | Validate empty mandatory fields | Negative | Critical | User on request form | Submit empty/incomplete form | Required messages display; no invalid request created | UI/API | Planned
PR-003 | PR-REQ-002 | Purchase Request | Reject zero or negative quantity | Boundary | Critical | Draft request form open | Enter 0 then negative quantity | Invalid quantities rejected | UI/API | Planned
PR-004 | PR-REQ-003 | Purchase Request | View saved purchase request | Positive | High | Draft request exists | Open from list | Header, lines, totals and status match stored data | UI/API | Planned
PR-005 | PR-REQ-003 | Purchase Request | Edit draft purchase request | Positive | High | Draft request exists | Change permitted line/header values; save | Changes persist and status remains valid | UI/API/DB | Planned
PR-006 | PR-REQ-004 | Purchase Request | Submit valid draft request | State transition | Critical | Valid Draft request exists | Submit and confirm | Status changes Draft to Submitted; history recorded | UI/API/DB | Planned
PR-007 | PR-REQ-004 | Purchase Request | Prevent duplicate submission | Concurrency | Critical | Valid Draft request exists | Submit twice or replay request | Single transition occurs; no duplicate workflow event | API/DB | Planned
PR-008 | PR-REQ-003 | Purchase Request | Prevent prohibited edit after submission | Negative | Critical | Submitted request exists | Attempt UI and direct API edit | Edit blocked according to status rule | UI/API | Planned
PR-009 | PR-REQ-005 | Purchase Request | Cancel eligible draft request | State transition | High | Draft request exists | Cancel and confirm | Status becomes Cancelled; history recorded | UI/API/DB | Planned
PR-010 | PR-REQ-006 | Purchase Request | Reject invalid status transition | Negative | Critical | Request in non-eligible status | Attempt unsupported status change via API | Request rejected and state remains unchanged | API/DB | Planned
APR-001 | APR-REQ-001 | Approval | Display submitted request in approval queue | Integration | Critical | Submitted request exists; approver authenticated | Open approval queue and locate request | Correct request is available to authorised approver | UI/API | Planned
APR-002 | APR-REQ-002 | Approval | Approve eligible purchase request | State transition | Critical | Submitted request; authorised approver | Approve request | Request becomes Approved and decision is recorded | UI/API/DB | Planned
APR-003 | APR-REQ-002 | Approval | Reject eligible request with reason | State transition | Critical | Submitted request; authorised approver | Enter reason and reject | Request becomes Rejected; reason persists | UI/API/DB | Planned
APR-004 | APR-REQ-002 | Approval | Validate mandatory rejection comment | Negative | High | Submitted request | Reject without required reason | Validation displayed; no decision committed | UI/API | Planned
APR-005 | APR-REQ-003 | Approval | Block unauthorised approval action | Security | Critical | Non-approver authenticated | Attempt approval in UI and API | Action denied; request unchanged; event safely logged | UI/API/DB | Planned
APR-006 | APR-REQ-003 | Approval | Prevent self-approval where segregation is required | Security | Critical | Requester is also approval-capable user | Requester attempts to approve own request | Action denied according to policy | UI/API | Planned
APR-007 | APR-REQ-004 | Approval | Verify approval history fields | Audit | High | Decision completed | Open history/read API | Actor, timestamp, decision and comment are accurate | UI/API/DB | Planned
APR-008 | APR-REQ-005 | Approval | Prevent duplicate approval | Concurrency | Critical | Submitted request | Double-click/replay approval | Only one decision is committed | API/DB | Planned
APR-009 | APR-REQ-005 | Approval | Reject approval of stale or cancelled request | Negative | Critical | Request status changed after page loaded | Attempt approval from stale page/request | Conflict returned; latest state preserved | UI/API/DB | Planned
PO-001 | PO-REQ-001 | Purchase Order | Create PO from approved purchase request | Positive | Critical | Approved request not yet converted | Create PO from request | One linked PO is created with correct supplier/lines | UI/API/DB | Planned
PO-002 | PO-REQ-001 | Purchase Order | Prevent PO from unapproved request | Negative | Critical | Draft/submitted/rejected request exists | Attempt PO creation | Creation denied; no PO committed | UI/API/DB | Planned
PO-003 | PO-REQ-002 | Purchase Order | Calculate line and order totals | Calculation | Critical | PO with multiple lines | Enter quantities/prices and save | Line totals and grand total are accurate | UI/API/DB | Planned
PO-004 | PO-REQ-003 | Purchase Order | View saved PO and source linkage | Positive | High | PO exists | Search and open PO | Saved values and source request reference are correct | UI/API | Planned
PO-005 | PO-REQ-003 | Purchase Order | Edit eligible PO | Positive | High | Editable PO exists | Change permitted data; save | Changes persist and history is recorded | UI/API/DB | Planned
PO-006 | PO-REQ-004 | Purchase Order | Require reapproval after material value increase | Risk/state | Critical | Approved PO exists | Increase quantity/value and save | PO leaves Approved and enters reapproval state | UI/API/DB | Planned
PO-007 | PO-REQ-004 | Purchase Order | Preserve previous approval history after reapproval trigger | Audit | High | Approved PO edited materially | Open approval/status history | Prior approval remains; new pending event recorded | UI/API/DB | Planned
PO-008 | PO-REQ-005 | Purchase Order | Cancel eligible purchase order | State transition | High | Eligible PO exists | Cancel and confirm | PO becomes Cancelled and downstream receipt is blocked | UI/API/DB | Planned
PO-009 | PO-REQ-006 | Purchase Order | Prevent duplicate PO for same approved request | Negative | Critical | Approved request already converted | Attempt second conversion | Duplicate PO rejected; original linkage retained | UI/API/DB | Planned
PO-010 | SYS-REQ-003 | Purchase Order | Prevent duplicate PO on double submission | Concurrency | Critical | Valid conversion action available | Double-click or replay create | At most one PO is committed | API/DB | Planned
GRN-001 | GRN-REQ-001 | Goods Receipt | Receive full eligible PO quantity | Positive | Critical | Approved/open PO; active warehouse | Receive entire outstanding quantity | GRN created; PO becomes fully received; stock updates once | UI/API/DB | Planned
GRN-002 | GRN-REQ-002 | Goods Receipt | Receive partial PO quantity | Positive | Critical | Open PO with outstanding quantity | Receive part of ordered quantity | Partial GRN created; remaining quantity is correct | UI/API/DB | Planned
GRN-003 | GRN-REQ-002 | Goods Receipt | Complete remaining quantity after partial receipt | Integration | Critical | Partially received PO exists | Receive exact remaining quantity | Second GRN created; PO becomes fully received | UI/API/DB | Planned
GRN-004 | GRN-REQ-003 | Goods Receipt | Prevent over-receipt | Negative | Critical | PO has known remaining quantity | Enter quantity above remaining | Receipt rejected; stock and PO unchanged | UI/API/DB | Planned
GRN-005 | GRN-REQ-003 | Goods Receipt | Reject zero or negative receipt quantity | Boundary | Critical | Eligible PO exists | Submit zero then negative quantity | Invalid values rejected; no GRN created | UI/API | Planned
GRN-006 | GRN-REQ-003 | Goods Receipt | Prevent receipt against cancelled or unapproved PO | Negative | Critical | Cancelled/unapproved PO exists | Attempt receipt | Receipt denied; inventory unchanged | UI/API/DB | Planned
GRN-007 | GRN-REQ-003 | Goods Receipt | Prevent duplicate goods receipt submission | Concurrency | Critical | Valid receipt ready | Double-click or replay identical request | One GRN and one inventory movement are committed | API/DB | Planned
GRN-008 | GRN-REQ-004 | Goods Receipt | Verify receipt audit and references | Audit | High | GRN exists | Open details and query record | GRN number, PO, warehouse, user and timestamp are correct | UI/API/DB | Planned
INV-001 | INV-REQ-001 | Inventory | Increase on-hand stock after valid receipt | Integration | Critical | Baseline stock known | Post valid GRN and compare stock | On-hand increases by accepted quantity exactly once | API/DB | Planned
INV-002 | INV-REQ-002 | Inventory | Update only selected item and warehouse | Integration | Critical | Multiple items/warehouses have baselines | Receive item into target warehouse | Only target item-location balance changes | API/DB | Planned
INV-003 | INV-REQ-003 | Inventory | Create linked inventory transaction | Audit | High | GRN posted | Inspect inventory ledger/history | Movement links to GRN/PO with correct quantity and timestamp | UI/API/DB | Planned
SEC-001 | SEC-REQ-001 | Security | Reject missing, expired or invalid authentication token | Authentication | Critical | Protected endpoint available | Call endpoint without token, with invalid token and with expired token | Every request is denied consistently without protected data disclosure | API | Planned
SEC-002 | SEC-REQ-001 | Security | Invalidate session after logout | Session | High | Authenticated user session exists | Logout then reuse previous session/token where applicable | Session is no longer accepted according to the configured token model | UI/API | Planned
SEC-003 | SEC-REQ-002 | Security | Prevent horizontal object-level access | Authorisation | Critical | Two users have different procurement records | Change document identifier to another user's restricted object | Access is denied without revealing restricted object content | API | Planned
SEC-004 | SEC-REQ-002 | Security | Prevent privilege escalation through direct API calls | Authorisation | Critical | Requester/non-approver authenticated | Call approve, cancel or status endpoints reserved for another role | Action is denied; document and audit state remain correct | API/DB | Planned
SEC-005 | SEC-REQ-003 | Security | Reject SQL-injection-style input safely | Input security | Critical | Synthetic malicious strings prepared | Submit payloads containing SQL metacharacters in supported text/search fields | Input is safely handled; no query manipulation, data leakage or server error occurs | UI/API/DB | Planned
SEC-006 | SEC-REQ-003 | Security | Prevent stored and reflected script execution | Input security | Critical | Synthetic script payload prepared | Submit payload in supplier/request text fields and render it in list/details | Payload is encoded/sanitised; no script executes | UI/API | Planned
SEC-007 | SEC-REQ-004 | Security | Verify cross-origin request policy | CORS/CSRF | High | Approved and unapproved origins identified | Send preflight and state-changing requests from disallowed origin | Disallowed origin is rejected; allowed origin remains functional | API | Planned
SEC-008 | SEC-REQ-004 | Security | Verify CSRF protection for cookie-based state changes | CORS/CSRF | High | Authentication model confirmed | Attempt forged cross-site state-changing request | Request is rejected or rendered non-exploitable by the chosen authentication design | API | Planned
SEC-009 | SEC-REQ-005 | Security | Prevent secrets and sensitive data in errors and logs | Data protection | Critical | Safe access to test logs available | Trigger validation and server errors; inspect response and permitted logs | No password, token, cookie, secret, stack trace or unnecessary personal data appears | API/Logs | Planned
SEC-010 | SEC-REQ-006 | Security | Enforce rate limiting on authentication and sensitive actions | Abuse protection | High | Rate-limit policy configured | Send repeated login/approval/create requests above threshold | Requests are throttled safely without corrupting transactions | API | Planned
SEC-011 | SEC-REQ-007 | Security | Protect approval and status audit history from ordinary modification | Audit integrity | Critical | Approval/status history exists | Attempt update/delete through UI and non-authorised API paths | Audit events cannot be altered by ordinary users; attempt is rejected/logged | UI/API/DB | Planned
SEC-012 | SEC-REQ-008 | Security | Prevent mass assignment of protected fields | API security | Critical | Create/update payload available | Add fields such as status, approver, created_by or privileged role to payload | Protected fields are ignored or rejected; server-controlled values remain correct | API/DB | Planned
SEC-013 | SEC-REQ-009 | Security | Verify essential browser and transport security headers | Configuration | High | Test environment served through deployment configuration | Inspect HTTPS and response headers | Configured HTTPS and applicable security headers meet the approved baseline | API/Browser | Planned
SEC-014 | SEC-REQ-010 | Security | Scan dependencies and repository for critical vulnerabilities and secrets | Supply chain | High | Approved scanners configured | Run dependency and secret scanning against the release candidate | No unresolved critical finding or committed secret remains | CI/CD | Planned
SYS-001 | SYS-REQ-001 | Cross-cutting | Handle backend validation error safely | Error handling | High | Invalid request prepared | Submit invalid payload | Useful error shown; no stack trace or secrets exposed | UI/API | Planned
SYS-002 | SYS-REQ-002 | Cross-cutting | Maintain complete document status history | Audit | High | Document moved through multiple states | Review chronological history | Every valid transition has actor, time, from/to state | API/DB | Planned
SYS-003 | SYS-REQ-004 | Cross-cutting | Block unauthenticated procurement API access | Security | Critical | No valid session/token | Call protected endpoints | Access denied consistently; no data disclosed | API | Planned
SYS-004 | SYS-REQ-003 | Cross-cutting | Preserve transaction integrity when downstream update fails | Recovery | Critical | Failure can be simulated safely | Trigger failure during multi-record operation | Transaction rolls back or enters recoverable documented state | API/DB | Planned
E2E-001 | E2E-REQ-001 | End-to-End | Complete approved procurement flow through inventory | End-to-end | Critical | Authorised test users; master data available | Create supplier; create/submit/approve PR; create/approve PO; receive goods; verify inventory | All documents link correctly; statuses and stock are correct; no duplicates | UI/API/DB | Planned
E2E-002 | E2E-REQ-001 | End-to-End | Reject/cancel path creates no PO or inventory | End-to-end negative | Critical | Authorised test users | Create and submit PR; reject or cancel; attempt downstream actions | No PO/GRN/stock movement created; audit trail complete | UI/API/DB | Planned

## Traceability
Requirements Traceability Matrix
Requirement ID | Area | Risk | Test Case IDs | Case count | Coverage status | Open defects | Notes
SUP-REQ-001 | Supplier | Critical | SUP-001 | 1 | Covered | 0
SUP-REQ-002 | Supplier | High | SUP-002, SUP-003, SUP-010 | 3 | Covered | 0
SUP-REQ-003 | Supplier | Critical | SUP-004 | 1 | Covered | 0
SUP-REQ-004 | Supplier | High | SUP-005, SUP-006 | 2 | Covered | 0
SUP-REQ-005 | Supplier | Critical | SUP-007, SUP-008, SUP-009 | 3 | Covered | 0
WH-REQ-001 | Warehouse | High | WH-001, WH-003 | 2 | Covered | 0
WH-REQ-002 | Warehouse | High | WH-002 | 1 | Covered | 0
PR-REQ-001 | Purchase Request | Critical | PR-001 | 1 | Covered | 0
PR-REQ-002 | Purchase Request | Critical | PR-002, PR-003 | 2 | Covered | 0
PR-REQ-003 | Purchase Request | High | PR-004, PR-005, PR-008 | 3 | Covered | 0
PR-REQ-004 | Purchase Request | Critical | PR-006, PR-007 | 2 | Covered | 0
PR-REQ-005 | Purchase Request | High | PR-009 | 1 | Covered | 0
PR-REQ-006 | Purchase Request | Critical | PR-010 | 1 | Covered | 0
APR-REQ-001 | Approval | Critical | APR-001 | 1 | Covered | 0
APR-REQ-002 | Approval | Critical | APR-002, APR-003, APR-004 | 3 | Covered | 0
APR-REQ-003 | Approval | Critical | APR-005, APR-006 | 2 | Covered | 0
APR-REQ-004 | Approval | High | APR-007 | 1 | Covered | 0
APR-REQ-005 | Approval | Critical | APR-008, APR-009 | 2 | Covered | 0
PO-REQ-001 | Purchase Order | Critical | PO-001, PO-002 | 2 | Covered | 0
PO-REQ-002 | Purchase Order | Critical | PO-003 | 1 | Covered | 0
PO-REQ-003 | Purchase Order | High | PO-004, PO-005 | 2 | Covered | 0
PO-REQ-004 | Purchase Order | Critical | PO-006, PO-007 | 2 | Covered | 0
PO-REQ-005 | Purchase Order | High | PO-008 | 1 | Covered | 0
PO-REQ-006 | Purchase Order | Critical | PO-009 | 1 | Covered | 0
GRN-REQ-001 | Goods Receipt | Critical | GRN-001 | 1 | Covered | 0
GRN-REQ-002 | Goods Receipt | Critical | GRN-002, GRN-003 | 2 | Covered | 0
GRN-REQ-003 | Goods Receipt | Critical | GRN-004, GRN-005, GRN-006, GRN-007 | 4 | Covered | 0
GRN-REQ-004 | Goods Receipt | High | GRN-008 | 1 | Covered | 0
INV-REQ-001 | Inventory | Critical | INV-001 | 1 | Covered | 0
INV-REQ-002 | Inventory | Critical | INV-002 | 1 | Covered | 0
INV-REQ-003 | Inventory | High | INV-003 | 1 | Covered | 0
SEC-REQ-001 | Security | Critical | SEC-001, SEC-002 | 2 | Covered | 0
SEC-REQ-002 | Security | Critical | SEC-003, SEC-004 | 2 | Covered | 0
SEC-REQ-003 | Security | Critical | SEC-005, SEC-006 | 2 | Covered | 0
SEC-REQ-004 | Security | High | SEC-007, SEC-008 | 2 | Covered | 0
SEC-REQ-005 | Security | Critical | SEC-009 | 1 | Covered | 0
SEC-REQ-006 | Security | High | SEC-010 | 1 | Covered | 0
SEC-REQ-007 | Security | Critical | SEC-011 | 1 | Covered | 0
SEC-REQ-008 | Security | Critical | SEC-012 | 1 | Covered | 0
SEC-REQ-009 | Security | High | SEC-013 | 1 | Covered | 0
SEC-REQ-010 | Security | High | SEC-014 | 1 | Covered | 0
SYS-REQ-001 | Cross-cutting | High | SYS-001 | 1 | Covered | 0
SYS-REQ-002 | Cross-cutting | High | SYS-002 | 1 | Covered | 0
SYS-REQ-003 | Cross-cutting | Critical | SUP-011, PO-010, SYS-004 | 3 | Covered | 0
SYS-REQ-004 | Cross-cutting | Critical | SYS-003 | 1 | Covered | 0
E2E-REQ-001 | End-to-End | Critical | E2E-001, E2E-002 | 2 | Covered | 0

## Execution
Manual and Automated Execution Register
Execution ID | Test Case ID | Build | Environment | Execution type | Executor | Execution date | Actual result | Status | Evidence link/path | Defect ID | Retest status | Comments
EXEC-001 | SUP-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-002 | SUP-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-003 | SUP-003 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-004 | SUP-004 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-005 | SUP-005 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-006 | SUP-006 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-007 | SUP-007 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-008 | SUP-008 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-009 | SUP-009 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-010 | SUP-010 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-011 | SUP-011 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-012 | WH-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-013 | WH-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-014 | WH-003 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-015 | PR-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-016 | PR-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-017 | PR-003 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-018 | PR-004 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-019 | PR-005 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-020 | PR-006 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-021 | PR-007 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-022 | PR-008 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-023 | PR-009 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-024 | PR-010 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-025 | APR-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-026 | APR-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-027 | APR-003 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-028 | APR-004 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-029 | APR-005 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-030 | APR-006 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-031 | APR-007 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-032 | APR-008 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-033 | APR-009 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-034 | PO-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-035 | PO-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-036 | PO-003 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-037 | PO-004 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-038 | PO-005 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-039 | PO-006 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-040 | PO-007 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-041 | PO-008 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-042 | PO-009 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-043 | PO-010 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-044 | GRN-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-045 | GRN-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-046 | GRN-003 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-047 | GRN-004 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-048 | GRN-005 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-049 | GRN-006 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-050 | GRN-007 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-051 | GRN-008 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-052 | INV-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-053 | INV-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-054 | INV-003 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-055 | SEC-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-056 | SEC-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-057 | SEC-003 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-058 | SEC-004 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-059 | SEC-005 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-060 | SEC-006 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-061 | SEC-007 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-062 | SEC-008 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-063 | SEC-009 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-064 | SEC-010 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-065 | SEC-011 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-066 | SEC-012 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-067 | SEC-013 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-068 | SEC-014 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-069 | SYS-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-070 | SYS-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-071 | SYS-003 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-072 | SYS-004 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-073 | E2E-001 |  |  | Manual |  |  |  | Not Run |  |  | Not Run
EXEC-074 | E2E-002 |  |  | Manual |  |  |  | Not Run |  |  | Not Run

## Defects
Procurement Defect Log
Defect ID | Title | Related Test ID | Requirement ID | Feature | Severity | Priority | Status | Build/Environment | Steps to reproduce | Expected | Actual | Owner | Retest result

## Security Tests
Phase 1 Functional Security Test Specification
Test Case ID | Requirement ID | Feature | Title | Type | Priority | Preconditions | Test steps | Expected result | Target layer | Execution status
SEC-001 | SEC-REQ-001 | Security | Reject missing, expired or invalid authentication token | Authentication | Critical | Protected endpoint available | Call endpoint without token, with invalid token and with expired token | Every request is denied consistently without protected data disclosure | API | Not Run
SEC-002 | SEC-REQ-001 | Security | Invalidate session after logout | Session | High | Authenticated user session exists | Logout then reuse previous session/token where applicable | Session is no longer accepted according to the configured token model | UI/API | Not Run
SEC-003 | SEC-REQ-002 | Security | Prevent horizontal object-level access | Authorisation | Critical | Two users have different procurement records | Change document identifier to another user's restricted object | Access is denied without revealing restricted object content | API | Not Run
SEC-004 | SEC-REQ-002 | Security | Prevent privilege escalation through direct API calls | Authorisation | Critical | Requester/non-approver authenticated | Call approve, cancel or status endpoints reserved for another role | Action is denied; document and audit state remain correct | API/DB | Not Run
SEC-005 | SEC-REQ-003 | Security | Reject SQL-injection-style input safely | Input security | Critical | Synthetic malicious strings prepared | Submit payloads containing SQL metacharacters in supported text/search fields | Input is safely handled; no query manipulation, data leakage or server error occurs | UI/API/DB | Not Run
SEC-006 | SEC-REQ-003 | Security | Prevent stored and reflected script execution | Input security | Critical | Synthetic script payload prepared | Submit payload in supplier/request text fields and render it in list/details | Payload is encoded/sanitised; no script executes | UI/API | Not Run
SEC-007 | SEC-REQ-004 | Security | Verify cross-origin request policy | CORS/CSRF | High | Approved and unapproved origins identified | Send preflight and state-changing requests from disallowed origin | Disallowed origin is rejected; allowed origin remains functional | API | Not Run
SEC-008 | SEC-REQ-004 | Security | Verify CSRF protection for cookie-based state changes | CORS/CSRF | High | Authentication model confirmed | Attempt forged cross-site state-changing request | Request is rejected or rendered non-exploitable by the chosen authentication design | API | Not Run
SEC-009 | SEC-REQ-005 | Security | Prevent secrets and sensitive data in errors and logs | Data protection | Critical | Safe access to test logs available | Trigger validation and server errors; inspect response and permitted logs | No password, token, cookie, secret, stack trace or unnecessary personal data appears | API/Logs | Not Run
SEC-010 | SEC-REQ-006 | Security | Enforce rate limiting on authentication and sensitive actions | Abuse protection | High | Rate-limit policy configured | Send repeated login/approval/create requests above threshold | Requests are throttled safely without corrupting transactions | API | Not Run
SEC-011 | SEC-REQ-007 | Security | Protect approval and status audit history from ordinary modification | Audit integrity | Critical | Approval/status history exists | Attempt update/delete through UI and non-authorised API paths | Audit events cannot be altered by ordinary users; attempt is rejected/logged | UI/API/DB | Not Run
SEC-012 | SEC-REQ-008 | Security | Prevent mass assignment of protected fields | API security | Critical | Create/update payload available | Add fields such as status, approver, created_by or privileged role to payload | Protected fields are ignored or rejected; server-controlled values remain correct | API/DB | Not Run
SEC-013 | SEC-REQ-009 | Security | Verify essential browser and transport security headers | Configuration | High | Test environment served through deployment configuration | Inspect HTTPS and response headers | Configured HTTPS and applicable security headers meet the approved baseline | API/Browser | Not Run
SEC-014 | SEC-REQ-010 | Security | Scan dependencies and repository for critical vulnerabilities and secrets | Supply chain | High | Approved scanners configured | Run dependency and secret scanning against the release candidate | No unresolved critical finding or committed secret remains | CI/CD | Not Run

## Risk Register
Phase 1 Procurement Quality and Security Risk Register
Risk ID | Risk statement | Category | Likelihood (1-5) | Impact (1-5) | Inherent score | Level | Treatment / control | Related requirements | Related tests | Owner | Residual risk | Status
R-001 | Unauthorised or self approval | Security | 3 | 5 | 15 | Critical | Role/API/object access and segregation tests | APR-REQ-003; SEC-REQ-002 | APR-005; APR-006; SEC-003; SEC-004 | Quality Engineer | Low | Open
R-002 | Duplicate document or inventory posting | Data integrity | 4 | 5 | 20 | Critical | Idempotency, uniqueness, replay and DB checks | SYS-REQ-003 | SUP-011; PR-007; APR-008; PO-010; GRN-007 | Developer | Medium | Open
R-003 | Invalid status transition | Workflow | 3 | 5 | 15 | Critical | Server-side transition enforcement and history | PR-REQ-006; SYS-REQ-002 | PR-010; SYS-002 | Developer | Low | Open
R-004 | Approved PO changed without reapproval | Financial control | 4 | 5 | 20 | Critical | Material-change reapproval and immutable history | PO-REQ-004 | PO-006; PO-007 | Product Owner | Low | Open
R-005 | Over-receipt or duplicate receipt | Inventory | 4 | 5 | 20 | Critical | Remaining quantity, concurrency and exactly-once posting | GRN-REQ-003; INV-REQ-001 | GRN-004; GRN-007; INV-001 | Developer | Medium | Open
R-006 | Wrong item or warehouse stock update | Inventory | 3 | 5 | 15 | Critical | Item/location reconciliation and source linkage | INV-REQ-002; INV-REQ-003 | INV-002; INV-003 | Quality Engineer | Low | Open
R-007 | Partial commit creates inconsistent records | Reliability | 3 | 5 | 15 | Critical | Transactional rollback and recovery tests | SYS-REQ-003 | SYS-004 | Developer | Medium | Open
R-008 | Broken object or role authorisation | Security | 3 | 5 | 15 | Critical | Negative access testing at UI and API layers | SEC-REQ-002 | SEC-003; SEC-004 | Technical Owner | Low | Open
R-009 | Injection or unsafe rendered content | Security | 3 | 5 | 15 | Critical | Parameterisation, validation and output encoding | SEC-REQ-003 | SEC-005; SEC-006 | Developer | Low | Open
R-010 | Sensitive data or secret exposure | Security | 3 | 5 | 15 | Critical | Response/log review, redaction and secret scanning | SEC-REQ-005; SEC-REQ-010 | SEC-009; SEC-014 | Technical Owner | Low | Open
R-011 | System degrades under concurrent processing | Performance | 3 | 4 | 12 | High | Baseline checks now; dedicated k6 test phase later | SYS-REQ-003 | PR-007; PO-010; GRN-007 | Technical Owner | Medium | Open
R-012 | Incomplete or misleading test evidence | Governance | 3 | 4 | 12 | High | Permanent IDs, evidence requirements and RTM | E2E-REQ-001 | E2E-001; E2E-002 | Quality Engineer | Low | Open

## Coverage
Feature Coverage and Execution Status
Feature | Planned cases | Critical cases | Executed | Passed | Failed | Blocked | Execution coverage
Supplier | 11 | 4 | 0 | 0 | 0 | 0 | 0%
Warehouse | 3 | 1 | 0 | 0 | 0 | 0 | 0%
Purchase Request | 10 | 7 | 0 | 0 | 0 | 0 | 0%
Approval | 9 | 7 | 0 | 0 | 0 | 0 | 0%
Purchase Order | 10 | 6 | 0 | 0 | 0 | 0 | 0%
Goods Receipt | 8 | 7 | 0 | 0 | 0 | 0 | 0%
Inventory | 3 | 2 | 0 | 0 | 0 | 0 | 0%
Security | 14 | 8 | 0 | 0 | 0 | 0 | 0%
Cross-cutting | 4 | 2 | 0 | 0 | 0 | 0 | 0%
End-to-End | 2 | 2 | 0 | 0 | 0 | 0 | 0%

## Summary
Phase 1 Quality Dashboard
Coverage KPI | Value | Risk / defect KPI | Value
Planned test cases | 74 | Security planned | 14
Critical test cases | 46 | Security executed | 0
Requirements | 46 | Security execution coverage | 0%
Mapped requirements | 46 | Open Critical defects | 0
Requirement design coverage | 100% | Open High defects | 0
Executed tests | 0 | Total logged defects | 0
Execution coverage | 0% | Closed defects | 0
Passed | 0 | Defect closure rate | 0%
Failed | 0 | Failed retests | 0
Blocked | 0 | Open Critical risks | 10
Pass rate | 0%
Critical pass rate | 0%
Automation coverage | 0%
RELEASE STATUS: NOT READY — becomes eligible for human approval only when Critical execution/pass targets, E2E tests, security gates, defect gates and traceability criteria are satisfied.

## Standards Sources
Standards and Reference Sources
Reference | Use | Official URL
ISO/IEC/IEEE 29119-2:2021 | Test processes and risk-based management | https://www.iso.org/standard/79428.html
ISO/IEC/IEEE 29119-3:2021 | Test documentation templates | https://www.iso.org/standard/79429.html
IEEE 829-2008 | Historical standard; superseded by ISO/IEC/IEEE 29119 | https://standards.ieee.org/standard/829-2008.html